FairPlay Platform

v5.9 Final — 16-Milestone Technical Implementation Plan

Engineering Reference  ·  Detailed Tasks + Acceptance Criteria  ·  2026

How to Use This Document

Each milestone has four sections: Objective, Technical Implementation Tasks, Deliverables, and Acceptance Criteria.

Acceptance Criteria are measurable pass/fail tests. Every criterion must pass before the next milestone begins. No exceptions.

Gate Blockers list conditions that lock the next milestone regardless of other progress.

Parallel tracks are indicated — Financial Core, Client, Infrastructure, Game, Blockchain, Security run simultaneously.

Total duration: 16 milestones across approximately 28 weeks.

# Overview — 16 Milestones

| MS | Title | Week | Phase | Gate Dependency |
| --- | --- | --- | --- | --- |
| M1 | Financial Core Foundation | W1~W2 | Foundation | Schema Review must PASS |
| M2 | Infrastructure + State Machine | W2~W3 | Foundation | M1 API docs complete |
| M3 | Texas Hold'em Complete | W3~W4 | Core Game | M2 infra live |
| M4 | 4 Card Games (Baccarat, Niu Niu, Dou Di Zhu, San Zhang) | W4~W5 | Core Game | M3 pattern validated |
| M5 | 4 More Games + Third-Party | W5~W6 | Core Game | M4 pattern stable |
| M6 | Jackpot Engine Complete | W6~W7 | Jackpot | M3~M5 games stable |
| M7 | Reinsurance + Insurance Complete | W7~W8 | Finance | M1 FC + M6 Jackpot |
| M8 | In-Table Chat + Social | W8~W9 | Social | M2 infra stable |
| M9 | VIP System + Pro Tracker | W9~W10 | Retention | M3 game + M6 Jackpot |
| M10 | Reputation + Anti-Bot + Peer Challenge | W10~W11 | Risk | M9 reputation base |
| M11 | Agent System | W11~W12 | Agent | M9 wallet isolation confirmed |
| M12 | Operations + Admin Panel | W12~W14 | Ops | M1 FC ledger complete |
| M13 | Risk Control + Anomaly Detection | W14~W15 | Risk | M10 Anti-Bot + M12 ops |
| M14 | League + Club System | W15~W16 | League | M2 dual-system base |
| M15 | Three-Node Multi-Region + Migration | W16~W17 | Infra | M2 single-node stable |
| M16 | Full QA + Security Audit + Launch | W17~W18 | Launch | ALL milestones green |

| M1 Week 1~2 | Financial Core Foundation — Accounts, Ledger, Settlement, Wallets |
| --- | --- |

Objective

Build the financial bedrock. Nothing else starts until the accounts/ledger schema passes review.

Iron Rule enforced from Day 1: all balance changes MUST go through transfer(). Direct UPDATE on balance fields is prohibited everywhere.

Gate: Schema Review must pass with all team leads before M2 begins.

## Technical Implementation Tasks

| Task | Detail | Owner |
| --- | --- | --- |
| accounts table | Create accounts collection: id (UUID), account_type ENUM (PLAYER/TREASURY/INSURANCE/REINSURANCE/LEAGUE_INVENTORY/JACKPOT_MINI/JACKPOT_MINOR/JACKPOT_MAJOR/JACKPOT_GRAND), owner_id (string), balance (BIGINT, cents), frozen_amount (BIGINT, default 0), version (INT optimistic lock), created_at, updated_at | FC Lead |
| ledger table | Create ledger collection: id (UUID), from_account (ref accounts.id), to_account (ref accounts.id), amount (BIGINT > 0), type ENUM (DEPOSIT/WITHDRAW/RAKE/BET/WIN_PAYOUT/INSURANCE_PREMIUM/INSURANCE_PAYOUT/REINSURANCE_INJECT/REINSURANCE_PAYOUT/JACKPOT_INJECT/JACKPOT_PAYOUT/LEAGUE_TOPUP/LEAGUE_CASHOUT/WITHDRAW_REFUND/AGENT_COMMISSION/AGENT_VIP_BONUS), idempotency_key (UNIQUE), status ENUM, metadata (JSONB), created_at | FC Lead |
| transfer() function | Implement as the ONLY way to move funds. Steps: (1) ClearingRules whitelist check, (2) idempotency_key Redis check (TTL 7d), (3) findOneAndUpdate with version check on from_account, (4) increment to_account balance, (5) insert ledger row — all in one MongoDB transaction. Non-whitelist flow: throw IllegalFundFlowError + write security_log + TG Bot alert. | FC Lead |
| ClearingRules whitelist | Hardcode ALLOWED_FLOWS object in source code (not DB, not config). Define all 6 source types and permitted destinations. Any flow not in whitelist: reject immediately. | FC Lead |
| Settlement Engine Phase 1 | Implement settleRound(): (1) calc winner_profit, (2) inject 0.5% to 4 JACKPOT accounts (Mini 20%/Minor 30%/Major 25%/Grand 25%), (3) rake to TREASURY or LEAGUE_INVENTORY per Settlement Domain, (4) payout to winner PLAYER, (5) write all ledger entries — all in one transaction ≤50ms. Generate settlement_receipt with accounts field. | FC Lead |
| Settlement Engine Phase 2 | Implement async queues: RAKE_QUEUE (Worker=5) for Platform Treasury aggregation, JACKPOT_QUEUE (Worker=3) for Jackpot pool updates. Queue backlog monitoring: >1000 alert, >5000 auto-scale. | FC Lead |
| Settlement Domain | Implement getRakeDestination(tableType, leagueId): platform→TREASURY, league→LEAGUE_INVENTORY. Used by Phase 1 to determine rake destination. | FC Lead |
| Withdrawal state machine | Implement 5-state machine: REQUESTED→APPROVED→BROADCASTING→CONFIRMED / FAILED→ROLLED_BACK. APPROVED: atomically deduct balance. ROLLED_BACK: atomically refund via transfer() type=WITHDRAW_REFUND. | FC Lead |
| frozen_amount lifecycle | Buy-in: atomically decrement balance + increment frozen_amount. Leave table: reverse. Withdrawal: uses balance only. Server restart: frozen_amount persists, auto-recovers. | FC Lead |
| Seven circuit breakers | Implement CB1~CB7: CB1 insurance pool level, CB2 daily payout rate >15%, CB3 Jackpot 3/hour same table, CB4 account abnormal withdrawal, CB5 platform withdrawal rate, CB6 non-whitelist flow (most critical), CB7 on-chain address mismatch. CB6+CB7: immediate reject + security log + TG Bot alert. | FC Lead |
| HD wallet mapping | Implement HD wallet derivation path mapping (BIP-44). Map each account_type to derivation path. Hot/warm/cold threshold monitoring: hot>$50K auto-aggregate to warm, warm>$500K manual approval to cold. | FC Lead |
| TRC20 deposit listener | Implement dual-listener (primary + 5-min scan backup). Official USDT contract whitelist only: TR7NHqjeKQxGTCi8q8ZY4pL8otSzgjLj6t. Mempool: record pending, NO credit. 20-block confirm: transfer() type=DEPOSIT with txHash as idempotency_key. BigInt for all amounts. | FC Lead |
| dataScopeMiddleware | Implement middleware: extract leagueId from JWT ONLY. Never from request body. Inject dataScope into req. All reconciliation APIs must use this middleware. | FC Lead |
| CI/CD + repo rules | Create Financial Core as separate repository. Enforce 2-reviewer requirement. Three-way access separation: no single person holds write-code + deploy-production + DB-access simultaneously. | Infra Lead |
| MongoDB baseline | Initialize MongoDB Replica Set from Day 1 (even single node). TLS + SCRAM-SHA-256 auth. Redis: TLS, requirepass, rename-command for FLUSHALL/CONFIG/DEBUG. All amounts: integer cents, no float. | Infra Lead |

## Deliverables

| Deliverable | Description |
| --- | --- |
| accounts collection | With all 9 account_type values, version, frozen_amount fields |
| ledger collection | With idempotency_key UNIQUE index, all 16 LedgerTypes |
| transfer() function | ClearingRules + idempotency + optimistic lock + atomic execution |
| Settlement Engine v1 | Phase 1 (≤50ms transaction) + Phase 2 (async queues) |
| Withdrawal state machine | 5 states, atomic deduct/refund |
| Seven circuit breakers | CB1~CB7, all wired to TG Bot alerts |
| TRC20 deposit listener | 20-block confirm, official contract only |
| Financial Core API document | Published by end of Week 1. All endpoints documented with request/response schema. |
| dataScopeMiddleware | JWT-based scope injection on all reconciliation APIs |

✅ Acceptance Criteria — MUST ALL PASS before next milestone begins 1. Schema Review: all team leads sign off on accounts + ledger + transfer() + ClearingRules design. GATE — M2 blocked until this passes. 2. transfer() test: attempt PLAYER→REINSURANCE flow → IllegalFundFlowError thrown + security_log entry created + TG Bot alert fires within 5 seconds. 3. 50-table concurrent settlement simulation: all MongoDB local transaction times ≤50ms, zero TransientTransactionError. 4. Idempotency test: call settleRound() twice with same idempotency_key → second call returns already-processed, ledger has ONE entry not two, balance updated once. 5. CB6 test: any non-whitelist transfer attempt → TG Bot alert within 5 seconds. 6. TRC20 deposit: Mempool detection → NO balance change. 20-block confirmation → balance credited via transfer(). txHash duplicate → rejected by unique index. 7. frozen_amount: player buys in $1,000 → balance -$1,000, frozen_amount +$1,000. Withdrawal attempt → available = balance (frozen excluded). Leave table → frozen_amount released. 8. Financial Core API document published and accessible to all team members.

🚫 Gate Blockers — Next milestone is LOCKED until these are resolved 1. Schema Review fails → M2 locked. Identify specific failure items, fix within 24 hours, re-review. 2. MongoDB Replica Set not initialized from Day 1 → all subsequent multi-node work is at risk. 3. transfer() function not enforced as sole balance-modification path → any direct UPDATE found in codebase is a blocker.

| M2 Week 2~3 | Infrastructure + State Machine + Blockchain Foundation |
| --- | --- |

Objective

Three-node infrastructure live. Unified State Machine operational. Solana contracts deployed. Blockchain 3-layer resilience wired.

Frontend connects to real FC APIs (not Mock). Optimistic UI framework confirmed working on physical device.

## Technical Implementation Tasks

| Task | Detail | Owner |
| --- | --- | --- |
| Singapore node baseline | AWS ap-southeast-1: MongoDB Primary (1P+2R), Redis Sentinel primary, Cloudflare Zero Trust tunnel, cloudflared mTLS with platform device certificate. nmap: zero open ports. | Infra |
| Tokyo node | AWS ap-northeast-1: MongoDB read replica, Redis local cache, Cloudflare Zero Trust. FC writes route to Singapore. | Infra |
| Hong Kong node | Aliyun HK: MongoDB read replica, Aliyun WAF + DDoS High Defense + CDN (no Cloudflare). FC writes route to Singapore. | Infra |
| WAL degradation strategy | Implement 3-tier: <30s buffer writes to local WAL (persisted disk), 30s-10min pause new tables, >10min global pause. WAL auto-replay on primary recovery. Idempotency key prevents duplicate replay. | Infra |
| getBestNode() algorithm | Calculate sum of all player latencies to each node. Select minimum total latency node. Called on table creation and on player join. Migration triggers: diff >15% AND interval >10 minutes. | Infra |
| Table migration safety window | Detect: hand settled + no Jackpot animation + no countdown + chat queue empty. Max wait 3 minutes then cancel. Pre-build hot-standby WebSocket on new node. Interruption target <500ms. Frontend: 'Optimizing connection...' — never show 'Disconnected'. | Infra |
| Unified State Machine | Implement BaseGame abstract class, StateMachine, TurnManager, EventBus, RoomManager. Enforce 3 iron rules at framework level: client read-only, state changes only through StateMachine, money only through FC API. 4-step new game integration protocol. | Game |
| Solana contracts devnet | Deploy commitRound + commitJackpot + settlement_receipt contracts to Solana devnet. settlement_receipt must include accounts field (accountId for each pool involved). All contracts: nonce anti-replay, caller restricted to platform_authority (2/3 multi-sig). | BC |
| Commit-Reveal async flow | T+0ms: deal cards immediately. T+0ms: async broadcast commitRound to Solana (decoupled). 32-slot background confirm. Commit timestamp must be < deal timestamp in all cases. | BC |
| drand integration | Multi-node concurrent requests (Promise.race). 5-second timeout → immediate KMS fallback. TCP warm-up: build connection ONLY, never pre-fetch values (pre-fetching allows cherry-picking — fairness violation). BLS signature verification on every response. | BC |
| Blockchain 3-layer resilience | L1: Priority Fee ×1.5. L2: ChainHealthMonitor every 30s → auto-switch Polygon if Solana confirmTime>30s or failureRate>5%. L3: RFC 3161 timestamp service (legally recognized). Verification page: reads chainUsed field, shows correct explorer link. | BC |
| WebSocket security | ECDH key negotiation per game round (forward secrecy). Message-level HMAC + auto-increment sequence number (anti-replay). 3 failures → disconnect TCP + ban hardware fingerprint 30min. Max message 64KB, max rate 100/s/connection. | Sec |
| Optimistic UI framework | Click → local state update 0ms → server confirm async. 99.9% consistent, rare mismatch → rollback. touchstart prediction: preload animation assets 100-200ms before click. Delta updates (50 bytes vs 500 bytes). MessagePack encoding. | Client |
| Frontend Mock → real API | Connect all frontend modules to real Financial Core APIs. Remove all Mock data. Test full flow: register → deposit → join table → hand settled → balance updated. | Client |

✅ Acceptance Criteria — MUST ALL PASS before next milestone begins 1. getBestNode(): 3 players with different latency profiles → returns minimum total latency node. 2. WAL test: disconnect Singapore 45s → Tokyo WAL buffers writes → Singapore reconnects → WAL replays → Ledger consistent, zero duplicates. 3. Table migration: safety window detected correctly, Jackpot pool 100% preserved, WebSocket interruption <500ms measured. 4. HK node: China mainland test client → latency <100ms, WebSocket stability >95% over 10-minute test. 5. Commit-Reveal: cards dealt at T+0ms (no Solana wait). Solana tx confirmed at ~T+13s in background. Commit timestamp < deal timestamp verified. 6. drand TCP warm-up: connection built but NO value pre-fetched. After warm-up, drand response time <100ms. 7. drand timeout: kill all drand endpoints → KMS fallback activates within 5 seconds, game continues uninterrupted. 8. Blockchain congestion: set Solana failureRate=100% → auto-switch to Polygon → verification page shows PolygonScan link. 9. Optimistic UI: action click → animation starts <50ms measured on physical device (not simulator). 10. nmap scan all three server IPs: zero open ports.

🚫 Gate Blockers — Next milestone is LOCKED until these are resolved 1. Solana devnet contract deployment fails → M3 Commit-Reveal integration blocked. 2. WAL replay produces duplicate Ledger entries → idempotency key fix required before M3. 3. HK node latency >100ms from mainland China → CDN routing fix before M3.

| M3 Week 3~4 | Texas Hold'em — Complete Implementation |
| --- | --- |

Objective

Texas Hold'em is the most complex game and the validator for ALL core systems. Insurance, Jackpot, provably fair, smoothness — all wired here first.

The Web2.0 smoothness framework integrates HERE. Not retrofitted later. Animation windows must be utilized from day one.

## Technical Implementation Tasks

| Task | Detail | Owner |
| --- | --- | --- |
| Hand evaluation | 7-card best-5 evaluator (Fisher-Yates shuffle on final_seed). All 5-card hand rankings. Tie-breaking rules. | Game |
| Game state machine | Pre-flop → Flop → Turn → River → Showdown. Blind structure (SB/BB/Straddle). Action sequence per street. Timeout auto-fold. | Game |
| Pot management | Main pot + side pots for multiple All-ins. Correct winner determination for each pot. Dead money handling. | Game |
| Per-table Jackpot accounts | Create 4 JACKPOT accounts per table on table creation: JACKPOT_MINI, JACKPOT_MINOR, JACKPOT_MAJOR, JACKPOT_GRAND (owner_id=tableId). Each with HD wallet derived address. Min thresholds: Mini $10 / Minor $50 / Major $200 / Grand $1,000. | Game |
| Jackpot injection | From winner_profit: inject 0.5% via 4 transfer() calls (Mini 20%, Minor 30%, Major 25%, Grand 25%) in Phase 1 settlement transaction. | Game |
| Jackpot triggers | Mini: every 25~35 rounds random. Minor: 80~120 rounds. Major: daily random. Grand: Saturday 18:00-23:00 window, 3-condition gate (pool ≥ threshold AND players present AND within window). Pool below threshold: skip, counter continues, no subsidy. | Game |
| Insurance (Underwriting Engine) | 5-step sequence: (1) Reserve Health Check (threshold = max(histMaxPayout×2, $10K platform / $1K league)), (2) Exposure Check (Redis risk budget lock TTL=30s), (3) Single Payout Check (≤reserve×5%), (4) Max Coverage, (5) Quote Generation. UI: final odds ONLY, never expose RiskFactor. | Game |
| Insurance activation rules | Exactly 2 players All-in in Main Pot → show insurance UI. 3+ players All-in → silently skip. After flop: no insurance. Turn cap ≤25% pot. River cap ≤50% pot. Premium deducted at All-in moment (NOT during Phase 1 settlement). | Game |
| Insurance pre-calculation | At flop and turn: background compute insurance quotes, cache in Redis TTL=60s. All-in reads from cache → <10ms response time. | Game |
| Animation windows | Flop animation (800ms) → background insurance pre-calc. All-in animation (600ms) → generate next round server_seed. Jackpot animation (3~10s) → pre-fetch drand + prepare next hand. Animation ends = next hand ready, zero gap. | Client |
| Disconnect handling | Timer pauses. 20s grace period. Check-round: auto-check after 10s. Per-hand cumulative cap: 60s. Per-hour limit: V1-V3=3, V4-V5=5. Verification timer continues during disconnect (reconnect gives remaining time). | Game |
| Smoothness layer | Optimistic UI wired. Sound effects: click→sound 0ms, deal→shuffle sound, chips fly. Lottie animations. Cards dealt one-by-one 150ms interval. Canvas rendering for game, HTML/CSS for UI. | Client |
| Provably fair wiring | Wire Commit-Reveal to Texas: server_seed generated, server_commit computed, deal immediately, async commitRound to Solana. settlement_receipt with accounts field → Solana async. randomSource field in receipt (drand or fallback_kms). | BC |
| Verification tool | 5-step verification UI (independent domain). Step 1: SHA256(server_seed)===server_commit. Step 2: drand.cloudflare.com/{round} matches. Step 3: recalculate final_seed → Fisher-Yates → matches deal. Step 4: Solana timestamp < game start. Step 5: probability_table_hash matches GitHub. KMS fallback branch: use AWS CloudTrail instead of drand step. | BC |

✅ Acceptance Criteria — MUST ALL PASS before next milestone begins 1. 9-player table: full hand from pre-flop to showdown, settlement correct, Jackpot injected from winner profit only (loser balances unchanged, verified in Ledger). 2. Side pot: 3-player All-in with different stack sizes → correct main pot and side pot distribution verified. 3. Insurance: 2-player All-in → quote displayed <30ms from cache. 3+ players All-in → zero insurance UI shown. 4. Settlement order: Jackpot inject → rake → payout — in this sequence, verified in Ledger entry timestamps. 5. Jackpot threshold: pool=$9 (below Mini $10) → skip trigger, counter+1, pool balance unchanged, no subsidy. 6. Animation window: Jackpot animation plays → next hand server_seed generated during animation → animation ends → cards dealt within 200ms. 7. Disconnect grace: disconnect during bet round → timer pauses → reconnect within 20s → full game state restored. 8. Provably fair: verification tool 5 steps all pass. Commit timestamp < deal timestamp confirmed on Solana. 9. Latency baseline documented: P99 card deal <200ms, P99 action response <50ms, P99 insurance quote <30ms.

🚫 Gate Blockers — Next milestone is LOCKED until these are resolved 1. Settlement order wrong (Jackpot after payout) → Phase 1 transaction rewrite required. M4 blocked. 2. Commit timestamp ≥ deal timestamp → critical fairness failure. M4 blocked. 3. Insurance deducted during Phase 1 settlement (not at All-in moment) → fix before M4.

| M4 Week 4~5 | 4 Card Games — Baccarat, Niu Niu, Dou Di Zhu, San Zhang |
| --- | --- |

Objective

4 games using the validated State Machine pattern from M3. Each gets per-table Jackpot (4 independent accounts). Game pattern must be stable enough for M5.

## Technical Implementation Tasks

| Task | Detail | Owner |
| --- | --- | --- |
| Baccarat | Player/banker/tie betting. Natural win check. Third-card rule. Auto-settlement. Min players: 1 (vs dealer). Effective volume coefficient: ×0.3. Wire Jackpot (4 accounts per table). | Game |
| Niu Niu | Banker bidding with dual-lock concurrency protection (Redis atomic SETNX). Card combination calculation (牛几 determination). Winner payout multiplier table. Min players: 3 (min 1 banker bid). Wire Jackpot. | Game |
| Dou Di Zhu | Landlord bidding phase. Card play legality validation (sequence/pair/triple/bomb/rocket rules). Pass/play logic. Min players: 3 fixed. Wire Jackpot. | Game |
| San Zhang | 3-card hand comparison (three-of-a-kind > straight flush > flush > straight > pair > high card). Min players: 2. Wire Jackpot. | Game |
| Per-table Jackpot isolation | Each table gets its own 4 JACKPOT accounts. Cross-game isolation: Baccarat table Jackpot pool has zero effect on Niu Niu table Jackpot pool. JACKPOT account owner_id = tableId (not gameType). | Game |
| Provably fair for all 4 | Wire Commit-Reveal to each game. Dealer-hand games (Baccarat, Niu Niu): commit dealer seed too. Verification tool: extend to support all game types. | BC |
| Smoothness for all 4 | Apply optimistic UI, animation windows, sound feedback to all 4 games. Same responsiveness target as Texas. | Client |
| Effective volume | Baccarat ×0.3, Niu Niu ×0.5. Applied in VIP progress calculation. Displayed as coefficient tooltip at table entry. | Game |
| Minimum player enforcement | Below minimum: table shows 'Waiting for players', does not auto-start. Dou Di Zhu with 2 players: rejected. | Game |

✅ Acceptance Criteria — MUST ALL PASS before next milestone begins 1. All 4 games: full hand played, Ledger correct, Jackpot injected from winner profit only. 2. Niu Niu banker bid concurrency: 3 simultaneous bid requests → exactly 1 succeeds, 2 rejected (Redis atomic confirmed). 3. Cross-game Jackpot: inject into Baccarat table Jackpot → Niu Niu table Jackpot unchanged (verified by account balance query). 4. Effective volume: Baccarat hand rake $10 → VIP progress logs $3 (×0.3). Niu Niu rake $10 → logs $5 (×0.5). 5. Provably fair: all 4 games produce valid settlement_receipt with commit timestamp < deal timestamp. 6. 12 tables per game × 4 games = 48 concurrent tables: P99 settlement <200ms, zero FC errors. 7. Dou Di Zhu with 2 players: start attempt rejected, 'Waiting for players' shown.

🚫 Gate Blockers — Next milestone is LOCKED until these are resolved 1. Niu Niu banker bid race condition not fixed → M5 blocked (same pattern repeats in other games). 2. Cross-game Jackpot contamination found → JACKPOT account scope must be fixed before M5.

| M5 Week 5~6 | 4 More Games + Third-Party Integration |
| --- | --- |

Objective

Complete all 9 games. Red Packet Minesweeper and Cowboy & Beauty are platform-built. Lottery and Slots are third-party API integrations.

By end of M5: all 9 games playable, all Jackpots running, all provably fair. New player: install to first hand <3 minutes.

## Technical Implementation Tasks

| Task | Detail | Owner |
| --- | --- | --- |
| Red Packet Minesweeper | Grid layout + mine placement (server-side). Grid hash committed on Solana BEFORE any player bets. Reveal mechanic, multiplier table, safe/mine resolution. Min players: 2. | Game |
| Cowboy & Beauty | Dealer cards + player cards + payout table. Odds freeze T-5 seconds before reveal (prevents late-bet manipulation). Min players: 1 (vs dealer). Wire Jackpot. | Game |
| Lottery connector | Standard REST/WebSocket adapter to third-party Lottery API. Game outcomes from third party, but Jackpot and settlement still go through Financial Core. Strict isolation: third-party failure must NOT affect FC. | Game |
| Slots connector | Same isolation pattern as Lottery. Third-party RTP documentation must be received and stored. Display RTP% in game lobby. | Game |
| Third-party failure isolation | Lottery or Slots API down: UI shows 'temporarily unavailable', other games continue, zero FC transaction errors. Test: kill third-party API → platform continues unaffected. | Game |
| Lobby system | Game selection UI, per-game Jackpot display (sum of all active table pools per game type, live update). Table filter: stakes / player count / Jackpot size. Winner ticker: real data from JACKPOT_PAYOUT Ledger entries. | Client |
| New player flow | Download → login (TG OAuth one-tap) → lobby loads → table found → buy-in → first hand. Total target: <3 minutes from install on 4G connection. | Client |
| Minimum player enforcement (all games) | Texas 2, Baccarat 1, Niu Niu 3, Dou Di Zhu 3, San Zhang 2, Red Packet 2, Cowboy & Beauty 1. Enforced at server level. | Game |

✅ Acceptance Criteria — MUST ALL PASS before next milestone begins 1. All 9 games: full hand played, Ledger correct, Jackpot injected from winner profit only. 2. Red Packet Minesweeper: grid hash on Solana BEFORE any bets. Hash matches revealed grid at showdown. 3. Cowboy & Beauty: odds freeze — bet placed <5s before reveal is rejected at server level. 4. Lottery API killed → UI shows unavailable, zero FC errors, other 8 games continue. 5. New player flow: install to first hand average <3 minutes measured on 4G (3 test runs, all <3 min). 6. 54 concurrent tables (6 per game × 9 games): P99 settlement <200ms, zero FC errors. 7. Winner ticker in lobby shows real data from Ledger JACKPOT_PAYOUT entries (not mock data).

🚫 Gate Blockers — Next milestone is LOCKED until these are resolved 1. Third-party API errors propagate into FC transactions → strict isolation fix required before M6. 2. New player flow >5 minutes → identify onboarding bottleneck before M6.

| M6 Week 6~7 | Jackpot Engine Complete — Grand Window, History, Animation Optimization |
| --- | --- |

Objective

Complete the Jackpot system end-to-end. Grand Saturday window with 3-condition gate. Full history (no time limit). Animation parallel optimization (zero gap between hands). On-chain Jackpot commitment.

## Technical Implementation Tasks

| Task | Detail | Owner |
| --- | --- | --- |
| Grand Saturday window | Cron detects Saturday 18:00-23:00 UTC+8. Random trigger time within window (not fixed). 3-condition gate: pool ≥ $1,000 AND players at table AND within window — ALL three required simultaneously. Table FROZEN (no players): skip, wait for next Saturday. | Game |
| Jackpot weight system | weight = base_weight × behavior_factor × non_collusion_factor. behavior_factor: normal=1.0, abnormal=0.5, collusion confirmed=0.0. non_collusion_factor: no association=1.0, GPS+IP/WiFi match=0.3. VIP bonus: V4 Jackpot weight +10%, V5 +25%. Weighted random selection among eligible players. | Game |
| Jackpot full history | All-time queryable from Ledger (type=JACKPOT_PAYOUT). No time limit. Player UI: default 30-day view + full date-range query entry. On-chain verification link permanent. Admin: per-table Jackpot balances (Mini/Minor/Major/Grand) real-time. | Game |
| Animation parallel optimization | During Mini animation (3s): prepare next hand server_seed + pre-fetch drand. During Grand animation (10s): prepare next hand + pre-fetch drand + broadcast settlement_receipt to Solana. Animation ends = next cards ready within 200ms. | Client |
| Jackpot on-chain commitment | commitJackpot for each Grand trigger on Solana. Payout amount + winner address + tableId + timestamp → on-chain verifiable. Verification tool: add Jackpot verification flow (4-step check). | BC |
| Below-threshold handling | Pool below min threshold: skip trigger, counter continues, zero subsidy, zero deferred payout. Platform NEVER injects funds into any Jackpot pool. | Game |
| FROZEN table handling | Table has no players: JACKPOT accounts status=FROZEN. No triggers fire. Pool balance preserved. On next player join: auto-unfreeze, continue accumulating. | Game |

✅ Acceptance Criteria — MUST ALL PASS before next milestone begins 1. Grand: pool=$1,050 + players at table + Saturday window simulated → fires within window at random time. 2. Grand: pool=$1,050 + NO players (FROZEN) → does NOT fire. 3. Grand: pool=$1,050 + players + NOT Saturday → does NOT fire. 4. Mini threshold: pool=$9 → skip, counter+1, pool unchanged, no subsidy. 5. Jackpot history: query all-time → all JACKPOT_PAYOUT entries returned. Query 30-day default → correct date filter. 6. Animation parallel: Grand animation ends at second 10 → next cards dealt within 200ms (measured). 7. Jackpot on-chain: commitJackpot tx on Solana for Grand trigger, verification tool shows winner address + payout amount. 8. Weight test: confirmed-collusion account (behavior_factor=0.0) → Jackpot weight=0, excluded from distribution.

🚫 Gate Blockers — Next milestone is LOCKED until these are resolved 1. Grand fires outside Saturday window → timezone logic bug, fix before M7. 2. Animation parallel: next hand not ready within 200ms → investigate before M7.

| M7 Week 7~8 | Reinsurance + Insurance Complete + Financial Safety |
| --- | --- |

Objective

Complete the full financial safety stack. Reinsurance pools (platform + league independent). Insurance clawback. All 7 circuit breakers tested under load. WORM storage for Ledger audit.

## Technical Implementation Tasks

| Task | Detail | Owner |
| --- | --- | --- |
| Reinsurance pools | Platform REINSURANCE account (owner_id=PLATFORM) + League REINSURANCE account (owner_id=leagueId). Each capped at 3× historical max single-day payout. Monthly clawback: INSURANCE net profit 20%/month → REINSURANCE via transfer(). 24-month repayment deadline. TREASURY→INSURANCE: requires multi-sig approval (extreme case only). | FC |
| Insurance clawback cron | Monthly cron on 1st of month: calculate Insurance net profit for prior month, transfer 20% to REINSURANCE. Log as type=REINSURANCE_INJECT. Track 24-month deadline. | FC |
| WORM storage | Ledger complete export: sign with AWS KMS (non-exportable CMK) → write to S3 Object Lock (compliance mode, 7-year retention). Reinsurance pool clawback records included. Ledger integrity: daily Merkle Tree Root written to Solana. | Sec |
| Merkle Root daily anchor | Daily cron: compute Merkle Root of all account balances → transfer to Solana. Anomaly detection: if root mismatches previous day's accounts delta → immediate alert + freeze all withdrawals. | FC |
| Circuit breaker full test | Test all 7 CBs under simulated conditions: CB1 pool below threshold, CB2 payout rate >15%, CB3 Jackpot 3/hour, CB4 account withdrawal, CB5 platform rate, CB6 non-whitelist (most critical), CB7 address mismatch. Each must fire alert within 30 seconds. | QA |
| Audit log to remote syslog | MongoDB Audit Log → real-time sync to remote syslog (append-only, no delete). DBA access to wallets/ledger: read-only enforced via MongoDB RBAC. All admin operations logged. | Sec |
| S3 WORM verification | Test: attempt to delete or modify S3 WORM object → rejected by Object Lock compliance mode. Verify 7-year retention policy active. | Sec |

✅ Acceptance Criteria — MUST ALL PASS before next milestone begins 1. CB1: Insurance INSURANCE balance drops to $9,500 (below $10K threshold) → insurance sales disabled immediately. 2. CB2: Daily payout artificially set to 16% of pool → insurance suspended 24h, CB2 alert fires. 3. CB3: Jackpot triggers 3 times in 60 minutes on same table → table Jackpot frozen, TG Bot alert within 30s. 4. CB6: Non-whitelist fund flow attempt → rejected + security_log entry + TG Bot alert within 5s. 5. Reinsurance: Insurance payout exceeds reserve → REINSURANCE transfer to INSURANCE → payout completes. Ledger shows full path. 6. WORM: S3 Object Lock deletion attempt → rejected. 7-year retention policy active. 7. Merkle Root: manually modify one account balance in DB → next daily Merkle Root mismatch → alert fires + withdrawal freeze. 8. DBA access test: attempt direct balance UPDATE via MongoDB shell → RBAC permission denied, logged.

🚫 Gate Blockers — Next milestone is LOCKED until these are resolved 1. Any circuit breaker failing to fire within 30 seconds → fix before M8. 2. WORM storage not enforcing retention → compliance failure, fix before M8.

| M8 Week 8~9 | In-Table Chat + Social Features |
| --- | --- |

Objective

Social layer complete. Agora voice compatibility MUST be confirmed on Day 1 of M8. Decision locked — no re-evaluation.

Chat namespace must be completely isolated from game state namespace. Chat crash must not affect game.

## Technical Implementation Tasks

| Task | Detail | Owner |
| --- | --- | --- |
| Agora compatibility test (DAY 1 MANDATORY) | Test Agora SDK microphone permission in TG Mini App WebView across all target TG client versions. PASS: use Agora for all platforms. FAIL: TG Mini App = text+emoji only, voice on iOS/Android native only. Decision locked by end of M8 Day 1. Document TG client version tested. | Client |
| In-table chat | Socket.io independent namespace (completely separate from game state namespace). 30-50 emoji sticker pack. XSS filter on all text. HTML rendering disabled. Chat crash: game state namespace unaffected. | Client |
| Voice chat | Based on Day 1 Agora decision: Agora SDK for iOS/Android. TG Mini App: text+emoji only if Agora incompatible. No other voice alternatives considered. | Client |
| Spectator mode | Separate Socket.io connection. 5-second delay on all messages. Max 20 spectators per table. Spectators: receive delayed messages, cannot send. Server-side enforcement (not just UI). | Client |
| Chat permissions by reputation | Very Poor (0-299): chat disabled. Poor (300-499): limited emojis only. Standard+: full chat. Reputation tier affects chat, never affects fund withdrawal. | Client |
| Message persistence | Chat messages stored 24 hours for league admin review (own league only). Platform: all chats 24 hours. Club admin: no chat access. Agent: no chat access. | Client |

✅ Acceptance Criteria — MUST ALL PASS before next milestone begins 1. Agora test result documented with TG client version tested. Decision locked Day 1 of M8. 2. Chat namespace crash (simulated): game continues, game state unaffected, zero errors in game log. 3. Spectator: message received after 5-second delay (measured). Send attempt from spectator → rejected at server (not just UI). 4. 9 players chatting + 3 spectators + game in progress: game P99 latency unchanged vs no-chat baseline. 5. Chat permissions: Very Poor reputation account → chat disabled, fund operations unaffected. 6. XSS: inject script tag in chat message → rendered as plain text, not executed.

🚫 Gate Blockers — Next milestone is LOCKED until these are resolved 1. Agora test not completed Day 1 → chat scope definition blocked for M8. 2. Chat namespace affects game state → critical isolation failure, fix before M9.

| M9 Week 9~10 | VIP System + Pro Tracker + Player Profile |
| --- | --- |

Objective

Complete VIP 5-tier system (no cashback, privilege-maximized). Pro Tracker as data moat. V5 instant auto-transfer. Dynamic opponent profiling.

Wallet isolation confirmed: league wallet shown ONLY in league context, NEVER in My page or agent dashboard.

## Technical Implementation Tasks

| Task | Detail | Owner |
| --- | --- | --- |
| VIP tier tracking | Cumulative volume tracking (permanent, never resets). Monthly volume tracking for retention. Effective volume: Texas×1.0, Baccarat×0.3, Niu Niu×0.5, Others×0.4. Calculated from Ledger (type=RAKE) directly — tamper-proof. | Game |
| VIP retention rules | Monthly miss → 30-day grace period (all privileges maintained). Grace period ends + still miss → drop ONE tier. Never drops to bottom in one step. Cumulative volume: permanent floor. | Game |
| V3 Pro Tracker | Own VPIP (voluntarily put in pot %), PFR (pre-flop raise %), funnel analysis, positional stats. Calculated from player's own hand history. Real-time. Displayed in dedicated dashboard tab. | Client |
| V4 privileges | Unlimited opponent tagging (stored per player, private). Deep hand history cloud export (CSV). Priority withdrawal queue (jump the line — sorting logic change, no extra cost). TG 1-on-1 concierge (dedicated TG account, 30-min SLA). | Client |
| V5 dynamic opponent profiling | H2H net result per opponent at table: query Ledger aggregate for all hands involving both players. Cache in Redis key h2h:{playerA}:{playerB}. Update async after each settled hand. Display at table for V5 players only. | Client |
| V5 instant auto-transfer | Within caps (single ≤$10K, 24h ≤$30K): APPROVED state auto-advances to BROADCASTING without human review. Risk controls CB4 and CB7 still execute. Block auto-transfer if: new device login within 24h OR IP change within 2h. | FC |
| V5 entry effect | Lottie animation JSON bundled and cached on client at login. Triggered by WebSocket player_joined event when joining_player.vip_tier==='V5'. Fires for ALL players at table within 200ms. | Client |
| Black Gold table | Tables with $200/$400+ blinds. Visible and accessible to V5 only. Non-V5 players: filtered at gateway level (not just client). V5 entry: full-screen animation plays. | Game |
| Player profile card | Nationality flag, VPIP, hands played, win rate (30-day), reputation tier icon, last 5 login locations. Forced public for all players at same table. Pop-up on avatar tap. Non-same-table players: cannot view. | Client |
| VIP progress display | 'My VIP' page: effective volume progress bar + $X remaining to next tier + estimated upgrade date + grace period warning (if in grace). Coefficient tooltip shown at table entry. | Client |
| Wallet isolation enforcement | League wallet balance: shown ONLY in Tab1 League/Club context. NEVER in My page, agent dashboard, or any other context. Enforced at API level (not just UI). | Client |

✅ Acceptance Criteria — MUST ALL PASS before next milestone begins 1. V3 Pro Tracker: VPIP calculated correctly from player's own 50-hand history. Displayed in dashboard. 2. V5 instant auto-transfer: $8,000 withdrawal → APPROVED auto-advances to BROADCASTING, TG arrives <15s (end-to-end measured). 3. V5 auto-transfer block: new device login → withdrawal request → held 24h (verified via attempt on new device). 4. V5 entry effect: V5 joins table → Lottie animation fires for ALL players at table within 200ms (measured). 5. H2H dynamic profiling: 10 hands between A and B → Redis cache updated → V5 sees correct net H2H result. 6. Black Gold table: non-V5 API request for V5 tables → empty response (filtered at gateway). 7. Wallet isolation: My page API response contains zero league wallet data. 8. VIP retention: monthly miss → 30-day grace (privileges intact). Grace expires + still miss → drop 1 tier only.

🚫 Gate Blockers — Next milestone is LOCKED until these are resolved 1. V5 auto-transfer bypassing CB4/CB7 risk controls → critical security failure, fix immediately. 2. League wallet appearing in My page → critical isolation failure, fix before M10. 3. Reputation score blocking withdrawal → critical failure, fix immediately regardless of milestone.

| M10 Week 10~11 | Reputation + Anti-Bot + Peer Challenge |
| --- | --- |

Objective

Complete the player integrity layer. Reputation score (500-start, five tiers). Anti-Bot behavioral detection. Peer Challenge with full ruleset including blowback and race condition fix.

Anti-Bot score and Reputation score are COMPLETELY INDEPENDENT systems. This must be enforced in code.

## Technical Implementation Tasks

| Task | Detail | Owner |
| --- | --- | --- |
| Reputation score system | New accounts start at 500. First 100 normal rounds: auto-advance to 700 (no manual trigger). 5 tiers: Very Poor (0-299)/Poor (300-499)/Average (500-699)/Good (700-899)/Excellent (900-1000). Affects: table access + chat. NEVER affects fund withdrawal (iron rule). | Game |
| Reputation deductions | Verification fail: -20 pts. Bot confirmed (human review): -150 pts. Collusion confirmed (human review): -200 pts (drops to Very Poor). Deduction only after human confirmation — never automatic from AI score alone. | Game |
| Reputation appeal | Appeal: TG message to CS. 72h human review. Success: points restored. Failure: maintained, no re-appeal for 30 days. | Game |
| Anti-Bot behavioral detection | Independent 0-100 score (separate from reputation). Detects: (1) reaction time distribution (fixed delay or perfect random = bot signature), (2) bet sizing precision (always exact GTO ratios), (3) continuous online >16h no fatigue flag, (4) decision time minimum 3s enforcement on complex boards (server rejects action if <3s), (5) double-confirm gap ≥1s (All-in/raise>100% pot). | Game |
| Peer challenge full ruleset | Unlimited different targets. Same target: 1/day (24h cooldown). Global cooldown per target: 60 min, 1 popup only regardless of challenger count. Post-pass protection: 60 min after passing. Blowback: B passes <10s → A blocked from challenging B that day. Cooldown race fix: B's protection = max(trigger_time+60min, last_pass_time+60min). | Game |
| Challenge verification images | Server-generated dynamically. No client cache. Random rotation + noise + color shift. OCR-resistant. Valid for 30 seconds only. | Game |
| Challenge disconnect handling | Verification timer continues during disconnect (does NOT pause). Reconnect within 20s: receives remaining verification time. | Game |
| Single-account-one-table | Redis INCR atomic check: same accountId cannot be in 2 tables simultaneously. Device fingerprint: same hardware ID = 1 active WebSocket connection. Redis failover: new join requests wait max 3 seconds. | Game |
| Associated account group | GPS AND (IP OR WiFi) two-dimension match → tag as group, Redis TTL 24h. Same table: prohibited. Different tables 1-3: allowed but non_collusion_factor=0.3 for Jackpot. 4th account in group: blocked from joining any table. Appeal: ops review 72h with different device fingerprint evidence. | Game |

✅ Acceptance Criteria — MUST ALL PASS before next milestone begins 1. New account plays 100 normal rounds → reputation auto-advances to 700 (no manual trigger, verified by checking reputation after exactly 100 rounds). 2. Collusion confirmed → reputation drops -200 (Very Poor tier). Withdrawal attempt → still succeeds (reputation never blocks funds). 3. Anti-Bot: server rejects action submitted <3s after complex board (All-in river scenario, measured). 4. Double-confirm: All-in second click arrives 0.8s after first → rejected. 1.2s → accepted. 5. Peer challenge blowback: B passes in 8 seconds → A's challenge attempt to B API → 'cooldown active' response. 6. Single-table: attempt to join 2 tables simultaneously → exactly 1 succeeds, 1 rejected (Redis atomic confirmed). 7. Associated group: 3 accounts at 3 different tables → 4th account join attempt → blocked. 8. Verification disconnect: player disconnects during 30s verification → reconnects at second 15 → gets remaining 15s.

🚫 Gate Blockers — Next milestone is LOCKED until these are resolved 1. Anti-Bot score deductions without human review → fix before M11. 2. Peer challenge timer pausing during disconnect → fix before M11.

| M11 Week 11~12 | Platform Agent System |
| --- | --- |

Objective

Complete agent system: 2-level structure, self-set sub-agent rates, real-time commission per hand, 4-tab dashboard.

Commission only from platform lobby rake. League rake is zero involvement for agents. This separation must be enforced at the Ledger level.

## Technical Implementation Tasks

| Task | Detail | Owner |
| --- | --- | --- |
| Agent data model | agents table: userId, commissionRate (30% base), parentAgentId (nullable), status. referral_bindings table: playerId, directAgentId, parentAgentId — set at registration, permanent, never changes. Sub-agent rate constraints: parent sets rate (5% to parent_rate-5%). Parent must keep ≥5% for themselves. | FC |
| distributeAgentCommission() | Wire into Settlement Engine Phase 2 (RAKE_QUEUE Worker). For each settled hand: lookup referralChain → calculate direct agent commission → calculate parent agent commission (if exists) → transfer() TREASURY→PLAYER for each. LedgerType: AGENT_COMMISSION. Idempotency key: roundId+agentId. | FC |
| League table isolation | League table rake → LEAGUE_INVENTORY. distributeAgentCommission() is NOT called for league table hands. Verified: no AGENT_COMMISSION Ledger entry for league table hands. | FC |
| VIP linkage monthly cron | Runs 1st of each month. Queries prior month: each agent's downline V4/V5 total AGENT_COMMISSION. Pays delta (target - actual) via transfer() TREASURY→PLAYER type=AGENT_VIP_BONUS. V4: ×1.10 target, V5: ×1.20 target. | FC |
| Agent Center dashboard | My page entry (approved agents only). 4 tabs: (1) Commission Overview: today/week/30d/all-time selector, total + direct + sub-agent breakdown, trend chart, VIP bonus row. (2) My Players: list with activity color (green/yellow/grey), filters, tap-to-expand lifetime stats. (3) Promotion Tools: primary link + multi-link management + sub-agent rate editor + promo materials. (4) Settlement Records: per-hand log + CSV export. | Client |
| Referral link system | UUID + 32-char random salt. Permanent. New accounts only (existing accounts not re-bound). Multi-link: create named tracking links per channel, each tracked independently. | Client |
| Agent application workflow | Via TG CS or dedicated agent CS. Eligibility: reputation ≥700, no collusion, no Anti-Bot high-risk. 24-48h review. Approved: auto-generate link + agent agreement via TG Bot. | Ops |
| Agent permission boundaries | Agent CAN: view own downline volume/commission/VIP tier/activity. Agent CANNOT: view player balance, initiate withdrawal, operate league wallet, see other agents' data. Enforced at API level (dataScopeMiddleware for agents). | FC |

✅ Acceptance Criteria — MUST ALL PASS before next milestone begins 1. Commission per hand: rake $100, direct agent A (30%) → $30 credited to A's Platform Wallet within 5 seconds. 2. Sub-agent: rake $100, B rate=15% → B gets $15, A gets $15. Both credited within 5 seconds. 3. League table isolation: league table rake $100 → zero AGENT_COMMISSION entries in Ledger for that hand. 4. Agent data access: GET /player/:id/balance with agent token → 403 Forbidden. 5. Sub-agent rate edit: A sets B rate from 15% to 20% → next hand B gets 20%, A gets 10%. 6. VIP cron: V5 player prior month base commission $750 → cron pays delta $150 (AGENT_VIP_BONUS) on 1st of month. 7. Multi-link: Link A generates 5 registrations, Link B generates 3 → each link shows independent count.

🚫 Gate Blockers — Next milestone is LOCKED until these are resolved 1. Agent commission appearing from league tables → isolate by tableType before M12. 2. Agent able to view player balance → permission boundary failure, fix before M12.

| M12 Week 12~14 | Operations + Withdrawals + Admin Panel |
| --- | --- |

Objective

Platform ready to handle real-money operations. Withdrawal review queue, TRC20 monitoring hardening, league top-up workflow, admin panel.

## Technical Implementation Tasks

| Task | Detail | Owner |
| --- | --- | --- |
| Withdrawal review queue | Human review UI for ops: approve/reject with reason. Auto-approval for ≤$10K (non-V5). V5 ≤$10K: auto-BROADCASTING. >$10K: human review regardless of VIP. Review SLA: <5 minutes for auto-eligible. | Ops |
| Withdrawal address protection | Address modification: 48h cooldown. Player executes via link only — CS cannot modify directly. New device login: 24h withdrawal hold. IP change: 2h withdrawal hold. Notifications pushed for all holds. | FC |
| TRC20 monitoring hardening | Dual-listener: primary event listener + 5-min polling backup. Official contract whitelist. Non-official: log + TG notify player + no credit. Mempool: status=pending, no credit. 20-block confirm: credit. BigInt amounts. | FC |
| League top-up workflow | League admin requests top-up. Platform ops confirms TRC20 receipt. Ops executes transfer(TREASURY, LEAGUE_INVENTORY, amount, LEAGUE_TOPUP). Large top-up (>threshold): second ops person confirmation. Balance visible in league admin within 3 seconds. | Ops |
| League cash-out workflow | League admin requests cash-out. Platform ops reviews. transfer(LEAGUE_INVENTORY, TREASURY, amount, LEAGUE_CASHOUT). TRC20 sent to league registered address. 24h between cash-out requests. | Ops |
| Platform admin panel | Overview: total volume, rake, active players, Jackpot pool totals, pending withdrawals, risk alerts. Withdrawal queue: list, approve/reject, filter. Player search: full account detail. Risk event feed. | Client |
| League admin panel | League overview: volume, rake, player list, Jackpot balances. Top-up/cash-out request interface. Risk event feed: collusion alerts, verification failures, real-time push to league admin TG. | Client |
| TRC20 withdrawal execution | Hot wallet: auto-execute for amounts within cap. Warm wallet: 2/3 multi-sig for medium/large. Cold wallet: 3/5 multi-sig + offline process. Monitor hot wallet balance: auto-aggregate to warm when >$60K. | FC |

✅ Acceptance Criteria — MUST ALL PASS before next milestone begins 1. V5 withdrawal $5K: tap to TG notification <15 seconds (full end-to-end measured). 2. Non-official USDT contract deposit: zero credit, TG notification sent to player. 3. Mempool detected: status=pending only, no balance change. 20 blocks pass: balance credited. 4. CS attempt to modify withdrawal address via API: 403 Forbidden. 5. Large withdrawal >$10K: admin UI requires second ops person confirmation before APPROVED. 6. League top-up: balance visible in league admin within 3 seconds of ops confirmation. 7. DBA direct balance UPDATE attempt via MongoDB shell: RBAC rejects, logged to audit trail.

🚫 Gate Blockers — Next milestone is LOCKED until these are resolved 1. V5 auto-advance >$10K without ops confirmation → critical financial control failure. 2. TRC20 listener down without fallback activating → investigate dual-listener before M13.

| M13 Week 14~15 | Risk Control + Anomaly Detection + Collusion AI |
| --- | --- |

Objective

Complete risk control layer. Full Anti-Bot suite. Anomaly detection cron (MVP: Node.js, no Kafka). CB2 and CB3 auto-actions wired. Collusion AI with human-confirm-only ban policy.

## Technical Implementation Tasks

| Task | Detail | Owner |
| --- | --- | --- |
| Collusion detection AI | Score 0-100. 0-30: monitor. 31-70: auto-ban same table. 71-100: human review queue + restrict functions. AI score NEVER triggers account ban — human review confirmation required. Confirmed: chips seized (transfer to TREASURY or LEAGUE_INVENTORY by table type) + permanent ban. | Game |
| Anomaly detection cron | Node.js cron every 5 minutes. MongoDB aggregation pipeline. Checks: (1) payout rate >3σ from historical mean, (2) Jackpot trigger >3/hour same table, (3) volume anomaly >5× daily average single league, (4) H2H win rate anomaly, (5) Ledger balance vs account balance mismatch >$0.01. | FC |
| Alert delivery | Each anomaly: write to alerts collection → TG Bot webhook delivers to ops channel within 30 seconds. Auto-actions: CB3 fires → freeze table Jackpot. CB2 fires → suspend insurance 24h. All other anomalies: alert only, human decides. | FC |
| Full Anti-Bot suite wiring | Wire all Anti-Bot detection into real-time event processing: behavioral score update after each hand, associated group tag on table join, decision time enforcement on every action, double-confirm gap enforcement on All-in/raise. | Game |
| Reputation feeds Anti-Bot | Anti-Bot behavioral score threshold (>70) triggers human review queue. Human review: confirm bot → reputation -150. Confirm normal → no reputation change. AI never directly modifies reputation. | Game |
| Bot farm simulation test | Simulate 50 accounts with bot behavior patterns. Verify: behavioral scores elevate >70 within 20 hands per account. Human review queue populated. Ops can review and confirm/reject. Confirmed bots: permanent ban, chips seized to TREASURY. | QA |

✅ Acceptance Criteria — MUST ALL PASS before next milestone begins 1. CB3: Jackpot trigger 3 times in 60 minutes on same table → frozen + TG Bot alert within 30 seconds. 2. CB2: Insurance payout rate >15% → suspended 24h + alert fires. 3. Anomaly cron: manually inject balance mismatch $0.02 → alert fires within 5 minutes. 4. Associated group 4th account: GPS+IP match on 3 accounts already at 3 tables → 4th join blocked. 5. Bot farm simulation: 50 bot-pattern accounts → scores >70 within 20 hands → review queue populated. 6. Collusion confirmed: chips transfer to TREASURY (platform table) or LEAGUE_INVENTORY (league table) — correct routing verified. 7. AI score >70: triggers review queue (not auto-ban). Human confirms ban → then ban executes.

🚫 Gate Blockers — Next milestone is LOCKED until these are resolved 1. CB3 or CB2 auto-actions not firing reliably → cron execution must be confirmed before M14. 2. AI auto-banning without human review → policy violation, fix before M14.

| M14 Week 15~16 | League + Club System Complete |
| --- | --- |

Objective

Full league and club system. Complete dual-system isolation. League wallet context visible only inside league rooms. League applies to platform via TG.

## Technical Implementation Tasks

| Task | Detail | Owner |
| --- | --- | --- |
| League creation and application | League creation: apply via platform TG CS. League number assigned by platform. Club creation: apply within league. Club number assigned by league. League and club IDs are unique platform-assigned identifiers. | Game |
| League private rooms | League tables: visible only to league members. Completely invisible to lobby players — filtered at API gateway level (not just UI). Lobby GET /tables: zero league table rows. League member: sees league tables in league context only. | Game |
| Dual wallet context isolation | League wallet: shown only in Tab1 League/Club context inside specific league. NEVER in My page, NEVER in agent dashboard, NEVER in lobby. API enforcement: My page balance API returns platform wallet only. | Client |
| Club system | Club is nested under league. Club tables: subset of league tables. Club admin: dataScopeMiddleware restricts to own club data. Club inventory: subset of league inventory account. | Game |
| League autonomy settings | Self-service: rake rate (within platform min-max), table hours, buy-in minimums, spectator on/off. Rake rate change: 7-day transition period enforced by platform (cannot apply early). League agreement: sign clause prohibiting risk control exemption requests. | Game |
| League risk notifications | All risk events involving league players: push to league admin TG in real-time. League admin sees: collusion alerts, verification failures, withdrawal anomalies — for own league only (dataScopeMiddleware). | Game |
| League top-up/cash-out UI | League admin panel: request top-up (TRC20 payment instruction), view status, confirm receipt. Cash-out request with 24h cooldown. Balance visible in real-time after ops confirmation. | Client |
| League Jackpot isolation | League table Jackpots: independent per-table JACKPOT accounts under league context. Cannot be shared with or affected by platform table Jackpots. | Game |

✅ Acceptance Criteria — MUST ALL PASS before next milestone begins 1. Lobby player: GET /tables API → zero league table rows in response. 2. League member: league context → sees league tables. Lobby context → sees lobby tables. Never mixed. 3. My page balance API: zero league wallet data in response. 4. Tab1 League context: league wallet balance shown correctly. 5. Club admin dataScopeMiddleware: club admin request for other club's data → empty response. 6. Rake change 7-day enforcement: attempt to apply rake change immediately → rejected, scheduled for +7 days. 7. League Jackpot: Jackpot trigger on league table → league table pool only, platform tables unaffected.

🚫 Gate Blockers — Next milestone is LOCKED until these are resolved 1. League tables visible to lobby players via API → critical isolation failure, fix before M15. 2. League wallet visible in My page → isolation failure, fix before M15.

| M15 Week 16~17 | Three-Node Multi-Region + Dynamic Routing + Migration |
| --- | --- |

Objective

Promote single-node deployment to full three-node multi-region. Dynamic optimal routing live. Table migration with safety window. Latency SLAs met for all regions.

## Technical Implementation Tasks

| Task | Detail | Owner |
| --- | --- | --- |
| Singapore primary promotion | Promote Singapore to true primary: Financial Core main DB, Redis Sentinel primary, all FC writes routed here. Replica Set confirmed healthy (1P+2R). | Infra |
| Tokyo secondary | Confirm Tokyo read replica in sync with Singapore primary. Latency Japan/Korea players: <70ms to Tokyo node. FC writes from Tokyo: routed to Singapore. | Infra |
| Hong Kong secondary | Confirm HK read replica in sync. Aliyun WAF + DDoS High Defense + CDN confirmed working. Latency mainland China: <100ms to HK node. | Infra |
| getBestNode() live | Deploy getBestNode() algorithm to production. Test with real player latency data from all three regions. Verify routing decisions are correct. | Infra |
| Dynamic migration production | Table migration safety window detection live in production. Pre-built hot-standby WebSocket. Interruption <500ms target. Frontend 'Optimizing connection' display. | Infra |
| WAL degradation live | Simulate Singapore primary failure in staging environment: Tokyo + HK WAL activates, games continue, no player-visible errors. Singapore recovery: WAL replays, Ledger consistent. | Infra |
| Solana mainnet migration | Migrate Solana contracts from devnet to mainnet. Verify commitRound and settlement_receipt working on mainnet. Update all verification tool URLs to mainnet Solana Explorer. | BC |
| Latency SLA validation | Measure P99 latencies with players in all 3 regions simultaneously: Singapore <30ms, Thailand/Malaysia <80ms, Japan/Korea <70ms, China mainland <100ms. Document results. | QA |
| Multi-region load test | Simulate 100 players from each of the 3 regions simultaneously (300 total). 50 concurrent tables. Verify P99 settlement <200ms globally, zero FC errors, no cross-region data contamination. | QA |

✅ Acceptance Criteria — MUST ALL PASS before next milestone begins 1. getBestNode() production: players from Japan routed to Tokyo node. Players from China routed to HK node. Players from SEA routed to Singapore. Verified by node selection logs. 2. WAL simulation: Singapore down 45s → WAL active → recovery → Ledger consistent, zero duplicates. 3. Table migration production: trigger migration on active table → safety window detected → interruption <500ms → game continues seamlessly. 4. Latency SLA: P99 from mainland China to HK node <100ms. P99 Japan/Korea to Tokyo <70ms. All documented. 5. 300-player multi-region load: P99 settlement <200ms globally, zero FC errors, zero cross-region contamination. 6. Solana mainnet: commitRound tx on mainnet Solana Explorer. settlement_receipt visible on mainnet. 7. Solana verification tool: all links point to mainnet Explorer (not devnet).

🚫 Gate Blockers — Next milestone is LOCKED until these are resolved 1. WAL replay produces Ledger duplicates in production simulation → fix before M16. 2. Solana contracts still on devnet → mainnet migration required before M16 launch. 3. Any latency SLA miss → identify bottleneck and fix before M16.

| M16 Week 17~18 | Full QA + Security Audit + Launch Preparation |
| --- | --- |

Critical Rule: No new features in M16. Bug fixes only. Every M1~M15 acceptance criterion must be GREEN before M16 begins.

If any prior milestone has a red criterion: fix it before starting M16. Do not carry debt into launch.

M16 ends with Go/No-Go decision signed by all team leads. If Go/No-Go fails: identify blockers, fix, re-sign.

## Technical Implementation Tasks

| Task | Detail | Owner |
| --- | --- | --- |
| Financial Core integrity audit | 100-hand spot-check: every hand, verify Ledger has entries for ALL money movements (Jackpot inject + rake + payout + agent commission if applicable). Sum all Ledger entries per account = current account balance. ZERO discrepancy allowed. | QA |
| Security penetration test | Test all critical paths: (1) direct MongoDB balance UPDATE → RBAC rejects. (2) Non-whitelist transfer via API → IllegalFundFlowError. (3) Withdrawal address change via CS endpoint → 403. (4) leagueId injection via request body → JWT value used. (5) WebSocket message replay with old sequence → rejected. (6) ECDH session key reuse across rounds → rejected. Document all results. | Sec |
| Latency P99 measurement | 100 concurrent WebSocket connections, 50 tables active. Measure P99: card deal <200ms, action response <50ms, insurance quote <30ms, post-Jackpot next hand <200ms. ALL four must pass. Document results. | QA |
| Chaos engineering | Fully isolated environment, synthetic data ONLY. Test: (1) MongoDB primary fail → WAL → recovery → Ledger consistent. (2) drand all nodes fail → KMS within 5s → game continues. (3) Redis primary fail → Redlock releases → new lock. (4) Certificate expiry → alert fires, connection rejected. (5) Network partition between nodes → WAL activates, data consistent on recovery. | QA |
| Three-platform regression | iOS native app + Android native app + TG Mini App. All 9 games, full hand, withdrawal, deposit, VIP progress, agent dashboard, chat, spectator. ZERO P0 or P1 bugs on all 3 platforms. | QA |
| 9-game full regression | Every game, every edge case: Jackpot below threshold / insurance 3+ players / Grand window / disconnect mid-hand / associated account group block / V5 auto-transfer / peer challenge blowback. All documented with PASS/FAIL. | QA |
| App store submission | iOS App Store + Google Play. App size <100MB. Store listing assets (screenshots, description, multi-language). TG Mini App final deployment. Submit for review. | Client |
| Security whitepaper | Publish security whitepaper: provably fair mechanism, fund isolation architecture, audit trail chain, contact for security researchers. | Sec |
| Hot wallet funding | Confirm hot wallet funded within $50K cap. Warm wallet funded. Cold wallet balance confirmed by multi-sig holders (3/5 signers confirm). | FC |
| Ops readiness | Withdrawal queue staffed. League admin contacts onboarded and trained. TG Bot alerts configured and tested. On-call rotation defined. | Ops |

✅ Acceptance Criteria — MUST ALL PASS before next milestone begins 1. Ledger integrity: 100-hand spot-check → sum of all Ledger entries per account = current balance. ZERO discrepancy. 2. Security pen test: all 6 critical paths tested and documented. All pass. 3. P99 latency: card deal <200ms, action <50ms, insurance <30ms, post-Jackpot <200ms. ALL four pass (documented). 4. Chaos engineering: all 5 scenarios pass. Ledger consistent in all recovery scenarios. 5. Three platforms: ZERO P0 bugs, ZERO P1 bugs (iOS / Android / TG Mini App). 6. Solana: contracts on mainnet (not devnet). Verified by mainnet Explorer tx hash. 7. Hot wallet: balance within $50K cap. Multi-sig holders confirm cold wallet balance. 8. All M1~M15 acceptance criteria: GREEN. No red items carried into launch. 9. Go/No-Go: all team leads sign off. Launch approved.

🚫 Gate Blockers — Next milestone is LOCKED until these are resolved 1. ANY Ledger discrepancy → launch blocked. Root cause must be found and fixed. 2. ANY P0 bug on any platform → launch blocked. 3. Latency P99 failure → profile and fix, re-measure. Cannot launch above targets. 4. Solana contracts still on devnet → mainnet migration required before launch. 5. Any M1~M15 acceptance criterion still red → fix before Go/No-Go.

# Master Acceptance Criteria — All 16 Milestones

This table is the launch checklist. Every item must be GREEN (checked) before launch. Print this page and use it as the sign-off sheet.

| MS | Criterion | Owner | Pass |
| --- | --- | --- | --- |
| M1 | Schema Review: all team leads sign off on accounts/ledger/transfer()/ClearingRules | FC Lead | ☐ |
| M1 | transfer() test: non-whitelist flow → error + security log + TG alert within 5s | FC Lead | ☐ |
| M1 | 50-table concurrent settlement: all ≤50ms, zero TransientTransactionError | FC Lead | ☐ |
| M1 | Idempotency: duplicate settleRound → already-processed, ONE Ledger entry | FC Lead | ☐ |
| M1 | frozen_amount: buy-in deducts balance + increments frozen. Withdrawal uses balance only. | FC Lead | ☐ |
| M1 | TRC20: Mempool → no credit. 20-block confirm → credit. txHash duplicate → rejected. | FC Lead | ☐ |
| M2 | getBestNode(): returns minimum-latency node for test scenario | Infra Lead | ☐ |
| M2 | WAL: Singapore down 45s → WAL → recovery → Ledger consistent, zero duplicates | Infra Lead | ☐ |
| M2 | Commit-Reveal: commit timestamp < deal timestamp on Solana | BC Lead | ☐ |
| M2 | drand timeout 5s → KMS activates, game continues uninterrupted | BC Lead | ☐ |
| M2 | Optimistic UI: action click → animation <50ms on physical device | Client Lead | ☐ |
| M3 | 9-player Texas: full hand, Jackpot from winner profit only, Ledger correct | Game Lead | ☐ |
| M3 | Settlement order: Jackpot inject → rake → payout (always this sequence) | FC Lead | ☐ |
| M3 | Insurance: 2-player All-in → quote <30ms. 3+ players → no UI shown. | Game Lead | ☐ |
| M3 | Provably fair: verification tool 5 steps all pass | BC Lead | ☐ |
| M3 | Jackpot pool $9 (below $10 threshold): skip, counter+1, no subsidy | Game Lead | ☐ |
| M4 | 4 games: Ledger correct, Jackpot from winner only, all pass | Game Lead | ☐ |
| M4 | Niu Niu concurrent banker bid: exactly 1 of 3 simultaneous bids succeeds | Game Lead | ☐ |
| M5 | All 9 games playable, all Jackpots running, all provably fair | Game Lead | ☐ |
| M5 | New player flow: install to first hand <3 minutes (4G, measured) | Client Lead | ☐ |
| M6 | Grand: fires within Saturday window (3-condition gate verified) | Game Lead | ☐ |
| M6 | Grand: missing any 1 condition → does NOT fire | Game Lead | ☐ |
| M6 | Animation parallel: next cards dealt <200ms after Jackpot animation ends | Client Lead | ☐ |
| M7 | CB1: Insurance drops below threshold → sales disabled immediately | FC Lead | ☐ |
| M7 | CB3: Jackpot 3/hour same table → frozen + TG alert within 30s | FC Lead | ☐ |
| M7 | WORM: S3 deletion attempt → rejected. 7-year retention active. | Sec Lead | ☐ |
| M8 | Agora decision locked Day 1 of M8 (documented) | Client Lead | ☐ |
| M8 | Chat namespace crash: game state unaffected | Infra Lead | ☐ |
| M9 | V5 withdrawal $5K: TG notification <15s (end-to-end) | FC Lead | ☐ |
| M9 | V5 entry effect: fires for all table players within 200ms | Client Lead | ☐ |
| M9 | Reputation: collusion confirmed → withdrawal still succeeds | FC Lead | ☐ |
| M9 | League wallet: zero data in My page API response | Client Lead | ☐ |
| M10 | New account 100 rounds → reputation auto-advances to 700 | Game Lead | ☐ |
| M10 | Peer challenge blowback: B passes <10s → A blocked from challenging B that day | Game Lead | ☐ |
| M10 | Single-table: simultaneous join → exactly 1 succeeds | Game Lead | ☐ |
| M11 | Commission per hand: $30 credited within 5s of $100 rake | FC Lead | ☐ |
| M11 | League table rake: zero AGENT_COMMISSION entry in Ledger | FC Lead | ☐ |
| M11 | Agent balance request: 403 Forbidden | Sec Lead | ☐ |
| M12 | V5 withdrawal $5K: tap to TG notification <15s | FC Lead | ☐ |
| M12 | Non-official USDT: zero credit, TG notification sent | FC Lead | ☐ |
| M12 | DBA direct balance UPDATE: RBAC rejects + audit log entry | Sec Lead | ☐ |
| M13 | CB3: 3 Jackpot triggers/hour → frozen + alert within 30s | FC Lead | ☐ |
| M13 | AI score >70: review queue triggered (no auto-ban) | Game Lead | ☐ |
| M14 | Lobby player: GET /tables → zero league tables in response | Game Lead | ☐ |
| M14 | League wallet: shown only in league context, never in My page | Client Lead | ☐ |
| M15 | Multi-region load 300 players: P99 settlement <200ms globally | Infra Lead | ☐ |
| M15 | Solana contracts on mainnet (verified by mainnet Explorer) | BC Lead | ☐ |
| M16 | Ledger integrity: 100-hand check, zero discrepancy | QA Lead | ☐ |
| M16 | Security pen test: all 6 paths pass (documented) | Sec Lead | ☐ |
| M16 | P99 latency: deal <200ms, action <50ms, insurance <30ms, post-Jackpot <200ms | QA Lead | ☐ |
| M16 | Chaos engineering: all 5 scenarios pass | QA Lead | ☐ |
| M16 | Three platforms: zero P0, zero P1 (iOS/Android/TG Mini App) | QA Lead | ☐ |
| M16 | All team leads: Go/No-Go signed | All Leads | ☐ |

FairPlay Platform  v5.9-FINAL  —  16-Milestone Technical Implementation Plan  —  2026

16 Milestones  ·  54 Acceptance Criteria  ·  No milestone advances without green gate  ·  Engineering Team